## Checklist
Software QA Checklist
Project Name |  | Todo application
Tester Name |  | Ahmad albdoor
Software Version |  | V 1.0
Date |  | 20/01/2025
ID | Test Suite | Test Title | Pre-Condition | Test Steps | Test Data | Expected result | Actual Result | Status
TC_001 | Signup | Signup should not be possible with an empty first name | To be in the signup page | 1- Keep the first name empty. 2- Fill a correct last name. 3- Fill a correct email formate, and the email should not be registered in the database. 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: Keep empy 2- Last name: albdoor 3- temail: test@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Should show this error "First Name is required, and it should be more than 3 characters" | This error message was displayed "First Name is required, and it should be more than 3 characters" | PASS
TC_002 | Signup | Signup should not be possible with a name with 2 characters | To be in the signup page | 1- Enter a first name with two characters 2- Fill a correct last name. 3- Fill a correct email formate, and the email should not be registered in the database. 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: AH 2- Last name:albdoor 3- temail: test1@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Should show this error "First Name is required, and it should be more than 3 characters" | This error message was displayed "First Name is required, and it should be more than 3 characters" | PASS
TC_003 | Signup | Signup should be posible if the first name is equal to 3 characters | To be in the signup page | 1- Enter a first name with three characters. 2- Fill a correct last name. 3- Fill a correct email formate, and the email should not be registered in the database. 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name:AHM 2- Last name: albdoor 3- temail: test2@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Should signup the user correctly | This error message was displayed "First Name is required, and it should be more than 3 characters" | FAIL
TC_004 | Signup | Signup should be posible if the first name is equal to 4 characters | To be in the signup page | 1- Enter a first name with four characters 2- Fill a correct last name. 3- Fill a correct email formate, and the email should not be registered in the database. 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: AHMA 2- Last name: albdooe 3- temail: test3@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Should signup the user correctly | Signup was correct | PASS
TC_005 | Signup | Signup should not be possible with an empty last name | To be in the signup page | 1- Fill a correct first name. 2- keep last name empty 3- Fill a correct email formate, and the email should not be registered in the database. 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: ahmad 2- Last name: empty 3- temail: test@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Should show this error "last Name is required, and it should be more than 3 characters" | It showed the correct error | PASS
TC_006 | Signup | Signup should not be possible with a last name with 2 characters | To be in the signup page | 1- Fill a correct first name. 2- Fill last name with 2 characters 3- Fill a correct email formate, and the email should not be registered in the database. 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: ahmad 2- Last name: HA 3- temail: test1@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Should show this error "last Name is required, and it should be more than 3 characters" | It showed the correct error | PASS
TC_007 | Signup | Signup should be posible if the last name is equal to 3 characters | To be in the signup page | 1- Fill a correct first name. 2- Fill last name with 3 characters 3- Fill a correct email formate, and the email should not be registered in the database. 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: ahmad 2- Last name: albd 3- temail: test2@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Should signup the user correctly | The signup was correct | PASS
TC_008 | Signup | Signup should be posible if the last is equal to 4 characters | To be in the signup page | 1- Fill a correct first name. 2- Fill last name with 4 characters 3- Fill a correct email formate, and the email should not be registered in the database. 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: ahmad 2- Last name: albdoor 3- temail: test3@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Should signup the user correctly | The signup was correct | PASS
TC_009 | Signup | Signup should not be possible if the email is invalid | To be in the signup page | 1- Fill a correct first name. 2- Fill la correct last name. 3- Fill a wrong email formate 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: ahmad 2- Last name: albdoor 3- temail: test3@.com 4- password: Test123! 5- confirm password: Test123! | Signup should fail | Signup failed | PASS
TC_010 | Signup | Signup should not be possible if the email is empty | To be in the signup page | 1- Fill a correct first name. 2- Fill la correct last name. 3- Fill an empty email 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: albdoor 2- Last name: ahmad 3- temail: tempty email 4- password: Test123! 5- confirm password: Test123! | Signup should fail | Signup Failed | PASS
TC_011 | Signup | Signup should not be possible if the email is exisit is the database | To be in the signup page | 1- Fill a correct first name. 2- Fill la correct last name. 3- Fill an email that is already registered in the database 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: ahmad 2- Last name:albdoor 3- temail: me@hatemhatamleh.com 4- password: Test123! 5- confirm password: Test123! | Signup should fail | Signup Failed | PASS
TC_012 | Signup | Signup should be possible if the email is correct and not registered in the database | To be in the signup page | 1- Fill a correct first name. 2- Fill la correct last name. 3- Fill a correct email that is not registered in the database 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: ahnad 2- Last name:albdoor 3- temail: test3@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Signup should work correctly | Signup was successfull | PASS
TC_013 | Signup | Signup should fail if the password is not in a valid formate | To be in the signup page | 1- Fill a correct first name. 2- Fill la correct last name. 3- Fill a correct email 4- Fill a not correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: ahmad 2- Last name: albdoor 3- temail: test4@gmail.com. 4- password: <One of the below> 5- confirm password: Test123! Passwords: "Test1234", "Test!!!!", "test1234!", "TEST1234!" | Signup should fail | Signup Failed | PASS
TC_014 | Signup | Signup should fail if the confirm password is not in a valid formate | To be in the signup page | 1- Fill a correct first name. 2- Fill la correct last name. 3- Fill a correct email 4- Fill a correct password. 5- Fill a not correct confirm password. 6- Click on signup button | 1- First name:ahmad 2- Last name: albdoor 3- temail: test4@gmail.com. 4- password: Test123! 5- confirm password: <One of the below> Passwords: "Test1234", "Test!!!!", "test1234!", "TEST1234!" | Signup should fail | Signup Failed | PASS
TC_015 | Signup | Signup should fail if both the password are in a good formate but not equal to each other | To be in the signup page | 1- Fill a correct first name. 2- Fill la correct last name. 3- Fill a correct email 4- Fill a correct password. 5- Fill a correct confirm password but not equal to the password. 6- Click on signup button | 1- First name: ahmad 2- Last name: albdoor 3- email: test3@gmail.com. 4- password: Test123! 5- confirm password: Test123!! | Signup should fail | Signup Failed | PASS
TC_016 | Signup | Signup should work correctly if the two passwords are in a correct formate and equal to each other | To be in the signup page | 1- Fill a correct first name. 2- Fill la correct last name. 3- Fill a correct email 4- Fill a correct password. 5- Fill a correct confirm password that is equal to the password. 6- Click on signup button | 1- First name:ahmad 2- Last name: albdoor 3- email: test3@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Signup should work correctly | Signup is correct | PASS
TC_017
TC_018
TC_019
Note on A6: A unique number for each test case
Note on B6: The test module, feature, condition, that can be divided into test cases
Note on C6: A short description of the test case, Anyone should be able to understand what we are going to test while reading it.
Note on D6: Any pre steps needed to start the test
Note on E6: The steps that we need to execute to do the test
Note on F6: The data that we are going to use while doing the steps
Note on G6: What is the expected output from the test
Note on H6: What is the expected output from the test

## Bug Report
Defect Report |  | Defect Report |  | Defect Report
Release | V.1.0 | Release | V.1.0 | Release | V.1.0
Title | User is not able to signup if he/she enters a first name with three charachters | Title | The location of the loader in the login page is wrong | Title | No available task message will appear when adding a total of 5 tasks
Description | It happens in all the browsers and all the screen views, the first name that we used during the testing is HAT | Description | After logging and while waiting the response from the server, the loader will appear in a wrong location, down with alot of margin | Description | In the todo page and when you add 5 todos, the message "No available tasks" will appear
Steps | 1- Enter a first name with "HAT". 2- Fill a correct last name. 3- Fill a correct email formate, and the email should not be registered in the database. 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | Steps | 1- Go to login page 2- Fill the email 3- Fill the password 4- Click on login 5- Check the loader | Steps | 1- Go to Todos Page 2- Add 5 tasks
Expected Results | Should be able to signup correctly | Expected Results | The loader should appear correctly in the correct location | Expected Results | No available tasks should not be visible
Actual Result | This error message was displayed "First Name is required, and it should be more than 3 characters" | Actual Result | The loader will be displayed in a wrong location | Actual Result | No available task is visible
Environment | Chrome V.97 | Environment | Chrome V.97 | Environment | Chrome V.97
Screenshot / Video |  | Screenshot / Video |  | Screenshot / Video
Rate | 2022-05-05 | Rate | 2022-05-05 | Rate | 2022-05-05
Priority | B | Priority | C | Priority | A
Status | Closed | Status | Closed | Status | Open
© Copy rights for QAcart 2022 |  | © Copy rights for QAcart 2022 |  | © Copy rights for QAcart 2022

## ID
Software QA Checklist
Project Name
Tester Name
Software Version
Date
ID | Test Suite | Test Title | Pre-Condition | Test Steps | Test Data | Expected result | Actual Result | Status
TC_001
TC_002
TC_003
Test case ID : is a unique number for each test case
© Copy rights for QAcart 2022

## Suite
Software QA Checklist
Project Name
Tester Name
Software Version
Date
ID | Test Suite | Test Title | Pre-Condition | Test Steps | Test Data | Expected result | Actual Result | Status
TC_001 | Login
TC_002 | Login
TC_003 | Login
Test Suite : The test module, feature, condition, that can be divided into test cases. So we group our test cases based on that suite
© Copy rights for QAcart 2022

## Title
Software QA Checklist
Project Name
Tester Name
Software Version
Date
ID | Test Suite | Test Title | Pre-Condition | Test Steps | Test Data | Expected result | Actual Result | Status
TC_001 | Login | Login with correct email and password
TC_002 | Login | Login with valid email and invalid password
TC_003 | Login | Login with valid email and empty password
Test case Title : A short description of the test case, Anyone should be able to understand what we are going to test while reading it.
© Copy rights for QAcart 2022

## PreCondition
Software QA Checklist
Project Name
Tester Name
Software Version
Date
ID | Test Suite | Test Title | Pre-Condition | Test Steps | Test Data | Expected result | Actual Result | Status
TC_001 | Login | Login with correct email and password | 1- User is at the Login page. 2- User is registered in the database
TC_002 | Login | Login with valid email and invalid password | 1- User is at the Login page. 2- User is registered in the database
TC_003 | Login | Login with valid email and empty password | 1- User is at the Login page. 2- User is registered in the database
Test Pre condition : Any pre steps needed to start the test
© Copy rights for QAcart 2022

## Test Steps
Software QA Checklist
Project Name
Tester Name
Software Version
Date
ID | Test Suite | Test Title | Pre-Condition | Test Steps | Test Data | Expected result | Actual Result | Status
TC_001 | Login | Login with correct email and password | 1- User is at the Login page. 2- User is registered in the database | 1- Fill the email input with a correct email. 2- Fill the password input with a correct password. 3- Click on Login Button
TC_002 | Login | Login with valid email and invalid password | 1- User is at the Login page. 2- User is registered in the database | 1- Fill the email input with a correct email. 2- Fill the password input with a wrong password. 3- Click on Login Button
TC_003 | Login | Login with valid email and empty password | 1- User is at the Login page. 2- User is registered in the database | 1- Fill the email input with a correct email. 2- Keep the password input empty. 3- Click on Login Button
Test Steps : The steps that we need to execute to do the test
© Copy rights for QAcart 2022

## Test data
Software QA Checklist
Project Name
Tester Name
Software Version
Date
ID | Test Suite | Test Title | Pre-Condition | Test Steps | Test Data | Expected result | Actual Result | Status
TC_001 | Login | Login with correct email and password | 1- User is at the Login page. 2- User is registered in the database | 1- Fill the email input with a correct email. 2- Fill the password input with a correct password. 3- Click on Login Button | Email: me@hatemhatamle.com Password: Test123!
TC_002 | Login | Login with valid email and invalid password | 1- User is at the Login page. 2- User is registered in the database | 1- Fill the email input with a correct email. 2- Fill the password input with a wrong password. 3- Click on Login Button | Email: me@hatemhatamle.com Password: Test123!!!!
TC_003 | Login | Login with valid email and empty password | 1- User is at the Login page. 2- User is registered in the database | 1- Fill the email input with a correct email. 2- Keep the password input empty. 3- Click on Login Button | Email: me@hatemhatamle.com Password: <Keep empty>
Test Data : The data that we need to execute the test case
© Copy rights for QAcart 2022

## Expected Result
Software QA Checklist
Project Name
Tester Name
Software Version
Date
ID | Test Suite | Test Title | Pre-Condition | Test Steps | Test Data | Expected result | Actual Result | Status
TC_001 | Login | Login with correct email and password | 1- User is at the Login page. 2- User is registered in the database | 1- Fill the email input with a correct email. 2- Fill the password input with a correct password. 3- Click on Login Button | Email: me@hatemhatamle.com Password: Test123! | It should go to the Todos page
TC_002 | Login | Login with valid email and invalid password | 1- User is at the Login page. 2- User is registered in the database | 1- Fill the email input with a correct email. 2- Fill the password input with a wrong password. 3- Click on Login Button | Email: me@hatemhatamle.com Password: Test123!!!! | It should return an error that the email or password is incorrect
TC_003 | Login | Login with valid email and empty password | 1- User is at the Login page. 2- User is registered in the database | 1- Fill the email input with a correct email. 2- Keep the password input empty. 3- Click on Login Button | Email: me@hatemhatamle.com Password: <Keep empty> | It should return an error that user must fill the password
Expected Result : The expected output of the software after executing the test steps
© Copy rights for QAcart 2022

## Actual Result
Software QA Checklist
Project Name
Tester Name
Software Version
Date
ID | Test Suite | Test Title | Pre-Condition | Test Steps | Test Data | Expected result | Actual Result | Status
TC_001 | Login | Login with correct email and password | 1- User is at the Login page. 2- User is registered in the database | 1- Fill the email input with a correct email. 2- Fill the password input with a correct password. 3- Click on Login Button | Email: me@hatemhatamle.com Password: Test123! | It should go to the Todos page | Todo page is visible
TC_002 | Login | Login with valid email and invalid password | 1- User is at the Login page. 2- User is registered in the database | 1- Fill the email input with a correct email. 2- Fill the password input with a wrong password. 3- Click on Login Button | Email: me@hatemhatamle.com Password: Test123!!!! | It should return an error that the email or password is incorrect | To do page is visible
TC_003 | Login | Login with valid email and empty password | 1- User is at the Login page. 2- User is registered in the database | 1- Fill the email input with a correct email. 2- Keep the password input empty. 3- Click on Login Button | Email: me@hatemhatamle.com Password: <Keep empty> | It should return an error that user must fill the password | error message is displayed
Actual Result : The Actual output of the software after executing the test steps
© Copy rights for QAcart 2022

## Test Status
Software QA Checklist
Project Name
Tester Name
Software Version
Date
ID | Test Suite | Test Title | Pre-Condition | Test Steps | Test Data | Expected result | Actual Result | Status
TC_001 | Login | Login with correct email and password | 1- User is at the Login page. 2- User is registered in the database | 1- Fill the email input with a correct email. 2- Fill the password input with a correct password. 3- Click on Login Button | Email: me@hatemhatamle.com Password: Test123! | It should go to the Todos page | Todo page is visible | PASS
TC_002 | Login | Login with valid email and invalid password | 1- User is at the Login page. 2- User is registered in the database | 1- Fill the email input with a correct email. 2- Fill the password input with a wrong password. 3- Click on Login Button | Email: me@hatemhatamle.com Password: Test123!!!! | It should return an error that the email or password is incorrect | To do page is visible | FAIL
TC_003 | Login | Login with valid email and empty password | 1- User is at the Login page. 2- User is registered in the database | 1- Fill the email input with a correct email. 2- Keep the password input empty. 3- Click on Login Button | Email: me@hatemhatamle.com Password: <Keep empty> | It should return an error that user must fill the password | error message is displayed | PASS
The Status : The Result of the test. Pass : The actual result equals the expected result Fail : The actual result does not equal the expected result N/A : Not applicable. N/E : Not executed
© Copy rights for QAcart 2022

## Status (hidden)
PASS
FAIL
N/A
N/E